## Sheet1
Complete
In Progress
|  |  |  | Not Started |  | Days in Sprint/Effort left
Sprint Backlog No. 2 | [5 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
Product Backlog | Description | Effort(person hours) | Responsible | Status | Status Notes | Mon | Tues | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed
1 | Design Interface |  |  |  | 1st user story
1.1 | Design app | 1 | ALL | Complete |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
1.2 | Implement design
1.2.1 | Main Page | 4 | Fraser | Complete |  | 4 | 7 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
1.2.2 | Alternate Pages | 4 | Euan | Complete |  | 4 | 6 | 6 | 5 | 5 | 6 | 4 | 3 | 3 | 3 | 2 | 1 | 0
1.2.3 | Connecting Pages | 2 | Sam | Complete |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
1.2.4 | Navigation | 2 | Giang | Complete |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Unit testing | 4 | Giang Candice | Complete |  | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
1.4 | Scrum | 3 | ALL | Complete |  | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
1.5 | Conversations | 2 | ALL | Complete |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| EFFORT TOTAL: | 22 |  |  | EFFORT REMAINING: | 22 | 24 | 21 | 19 | 18 | 16 | 14 | 13 | 12 | 11 | 7 | 5 | 1
[5 empty] | VELOCITY: | 22 | 20.1667 | 18.3333 | 16.5 | 14.6667 | 12.8333 | 11 | 9.1667 | 7.3333 | 5.5 | 3.6667 | 1.8333 | 2.2204e-15
2 | Estimate how much portfolio is worth |  |  |  | 2nd user story
2.1 | Display total of all stocks | 2 | Sam | In Progress |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1
2.2 | Message "The total for all shares is____" | 1 | Sam | In Progress | bar: Week 1 Mon to Week 3 Wed
2.3 | Error checking
2.3.1 | No available data | 2 | Euan | In Progress |  | 2 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1
2.3.2 | Can't connect to server | 2 | Fraser | Complete |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2.3.3 | Bad data | 2 | Giang | Complete |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2.4 | No decimal places | 1 | Candice | Complete |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Add comma for thousands | 1 | Candice | Complete |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.6 | Add date to prices | 3 | Candice | In Progress |  | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
2.7 | Converstations | 3 | ALL | In Progress |  | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1
2.8 | Scrum | 3 | ALL | Complete |  | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| EFFORT TOTAL: | 20 |  |  | EFFORT REMAINING: | 20 | 19 | 16 | 16 | 16 | 13 | 13 | 12 | 12 | 10 | 8 | 8 | 6
[5 empty] | VELOCITY: | 20 | 18.3333 | 16.6667 | 15 | 13.3333 | 11.6667 | 10 | 8.3333 | 6.6667 | 5 | 3.3333 | 1.6667 | -4.4409e-16
3 | Estimate how much each set of shares is worth in total |  |  |  | 3rd user story
3.1 | Updates prices within 15 minutes | 4 | Sam | Complete |  | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 1 | 0
3.2 | Calculates share total | 3 | Candice | In Progress |  | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
3.3 | Two decimal places | 1 | Candice | Complete |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | Error checking
3.4.1 | No available data | 2 | Euan | Complete |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3.4.2 | Can't connect to server | 2 | Fraser | Complete |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3.4.3 | Bad data | 2 | Giang | Complete |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| EFFORT TOTAL: | 14 |  |  | EFFORT REMAINING: | 14 | 13 | 9 | 9 | 8 | 8 | 7 | 7 | 7 | 7 | 5 | 4 | 4
[5 empty] | VELOCITY: | 14 | 12.8333 | 11.6667 | 10.5 | 9.3333 | 8.1667 | 7 | 5.8333 | 4.6667 | 3.5 | 2.3333 | 1.1667 | 1.3323e-15
| OVERALL EFFORT TOTAL: | 56 |  |  | OVERALL EFFORT REMAINING: | 56 | 56 | 46 | 44 | 42 | 37 | 34 | 32 | 31 | 28 | 20 | 17 | 11
[5 empty] | OVERALL VELOCITY: | 56 | 51.3333 | 46.6667 | 42 | 37.3333 | 32.6667 | 28 | 23.3333 | 18.6667 | 14 | 9.3333 | 4.6667 | 5.3291e-15